|  |  |  |
| --- | --- | --- |
| **GOAL 6:** Disseminate culturally responsive and universally accessible information about policies, promising practices, and emerging ideas that promote positive outcomes for people with disabilities and their families to at least 600,000 people over five years. | | |
| **Core Function: Information Dissemination**  **Areas of Emphasis: Areas of Emphasis:** Education and Early Intervention, Child Care, Quality Assurance, Health, Employment, and other- Quality of Life and Assistive Technology | | |
| **Type of Activity:** Advocacy, Capacity Building, Systemic Change | | |
| **Objectives (Annual Measures)** | **Major Accomplishments** | **FY 2015 Annual Progress Data** |
| **Obj. 6.1** Disseminate products, including presentations, publications, websites, white papers, literature reviews, program evaluations, curricula, research tools, brochures, media, fact sheets, public announcements, human interest stories, and other public awareness materials to at least 125,000 people annually using culturally responsive and multiple accessible formats. | CDHD faculty and staff disseminated 53 new products in FY 2015, which include:   1. 15 conference presentations 2. 3 distance learning modules 3. 7 electronic products 4. 3 newsletters 5. 6 brochures 6. 11 pamphlets, brochures, or fact sheets 7. 2 monographs 8. 1 website   A total of 18 additional products developed in previous years were also disseminated. Please see attachment for a list of all disseminated products. | 🞏Fully achieved  **🗹 Partially achieved**  🞏 Not initiated yet  **Goal 6 Overall: Partially Achieved**  **We disseminated at total of 71 products in FY 15 to a total of 77,124 people. 53 products were new and 18 were from previous years. A complete listing of products is attached. Since FY 2013 we have disseminated a total of 260,872 products.** |